****minutes

Sub project / GAP (incl. sub projects): GAP I

Date and location: 08.04.2022 Zoom

Participants: Marc Stamminger, Björn Eskofier, Christoph Ostgathe, Carsten Klein, Tobias Steigleder, Julia Yip, Markus Heyder, Ralf Müller, Vanessa Wirth, Falk Pulsmeyer

Keeper of the minutes: Falk Pulsmeyer

Date and location for next meeting: 13.05.2022 Zoom

|  |
| --- |
| **topic 1 – Bed Order** |
| content/description: |
| Two identical Beds for the “EmpkinS-Bed” One at the “EmpkinS-Lab” One at UKER |
| tasks and responsibilities:Two addresses for orderingOrder process in coordination with Judith |
| Stefan Grießhammer, Tobias Steigler |
|  |

|  |
| --- |
| **topic 2 – Topics Video Shoot**  |
| content/description: |
| Sensor and camera setupImportant movements to capture with the cameraHow to record Patients (especially Parkinson patient)Next steps for Data CollectionData Management |
| tasks and responsibilities:everyone |
|  |

|  |
| --- |
| **topic 3 – Early Study for D04** |
| content/description:Problem hardware delayed |
| Possible recordings with “old radar”sensors* Movement
* ECG
 |
| tasks and responsibilities: |
| Plan meeting with Tobias, Julia, Stefan, Björn, Jürgen Winkler, VanessaFalk Pulsmeyer,  |

|  |
| --- |
| **topics for next meeting** |
| 🞏 Research Data Management🞏 How to make data accessible for everyone🞏 Intermediate solution until next permanent one is found🞏 Meeting with Z-Project – (Coordination: Vanessa Wirth)🞏 Extend GAP Meeting to dicuss patient coordination |

**Notes:**